## Slide 1
Going For Gold
2011-2013
Comenius Multilateral School Partnership Project
CHECK LIST AND SUMMARY OF THE APPLICATION FORM
This project is funded by the European Commission
December 2011
D.Lavollée, French coordinator at the ISC
La Ville du Bois

## Slide 2
 | RESULTS AND OUTCOMES OF THE PROJECT GOING FOR GOLD 2011-2013
October 2011 | A "NING" site will be set up to promote regular communication between participants. Each student will be able to provide evidence of using the NING after each mobility. Video diaries, podcast, power-point presentations etc.
October 2011 | On going evaluation of the project will be available on NING, eg. Livre d'Or for comments by all community members about meetings
October 2011 | A protocol agreement of the safe use of the Internet will be available for parents, staff and students in all partner countries.
October 2012 | A Healthy school health check guide will be available and certificates awarded to successful partner schools.
June 2013 | The final visit will culminate in a public conference aimed at disseminating the benefits of the project to a wider audience and showcasing the learning achieved.
July 2013 | A minimum of 24 mobilities, involving staff and students ,from each school visiting each transnational partner school.
July 2013 | All students would have the opportunity of living with a host family in another cultural setting
July 2013 | All students will have taken part in activities which will have broadened their understanding of the opportunities that exist for employment, sport & leisure in other countries. Evidence showcased on NING with video diaries, podcasts and other media.
July 2013 | All staff will be able to report on examples of good practice they have observed and that they have adopted or intend to adopt in their own teaching.
July 2013 | All participants will have communicated with people from partner countries informally and formally in their mother tongue and in a foreign language.
July 2013 | All students will have made presentations to other participants, members of their school and wider community on how leisure and sporting activities help develop healthy lifestyles and careers & economic opportunities in their own countries.
July 2013 | All students will have produced a personal statement about " What I have learnt from the Comenius project".
July 2013 | Improved ICT skill and digital competencies for staff and students.
July 2013 | Final report and translations written by all the partners

## Slide 3
DURING THE 2 YEARS OF THE PROJECT

## Slide 4
THE COORDINATING SCHOOL : BRAUNTON SCHOOL AND COMMUNITY COLLEGE
1) The coordinating school will
- oversee the effective organization and responsibility for successful motilities, quality control and continued dialogue between partners throughout the project (NING, chats, videoconferences, Skype, letters, postcards and parcels)
have a monthly contact with each partner school to review progress and provide up-dates
contact each partner within two weeks of the mobility to check on progress
share with partner schools their experiences of “healthy school”
help to create “an own Comenius Healthy Schools Award” promoting sport, leisure, diet and active citizenship
organize training for the partnership during mobility visits
organize an audit of competences before the first visit so that a training schedule can be agreed
ensure that there are curriculum activities to facilitate group work and collaboration
invited staff, students and parents to join the NING community
publish the report of each mobility on the NING site
have overall responsibility for the NING and publish the progress on this site
organize the European final conference in July 2013
write the final report with all the partners

## Slide 5
2) Each school will
- adopt a healthy schools and Internet safety policy
report to school governing bodies, assemblies and curriculum enrichment days twice a year
- develop school notice boards which are owned by the students and which become their responsibility to update regularly
prepare joint reports enable the use of IT facilities for the common delivery of information to the proposed NING
complete a 'Livre d'Or‘ as part of the on-going evaluation process.
prepare school newsletters and websites to provide pupil feedback during mobilities
prepare a report of each mobility - details of the country visited, the focus of the visit, the activities that took place and any impact or outcomes that occurred
publish the report on the school web-site and NING site
send off the final report written and translated with all the partners
THE EUROPEAN PARTNER SCHOOLS

## Slide 6
3) A wide range of students will
participate actively in the proposed project partnership
be involved in working out plans for particular stages of the partnership
take responsibility for use of the proposed NING
exchange information before their mobility as well as using it as an evaluation tool to comment on aspects of the motilities that have been undertaken
make specific 'video diaries' of their experiences and on different subjects
increase linguistic and cultural awareness and use different language, particularly English, in real life situations
4) Pupils from Special Educational Needs (SEN) and from different socio-economic groups such as FSM (free school meals) will
- be actively engaged in the project and mobilities
STUDENTS

## Slide 7
We will have
- press and TV coverage (we have experience of this as part of previous projects) outlining visits, engagements etc.
- wider community involvement through the final conference in June 2013
- use and participation of local sporting and leisure facilities
- involvement of local sports people to give talks and master classes
- business breakfasts of local industries where students are introduced to world of work
- involvement of local employers to talk about skills they are looking for in their work force
- use of careers conferences within appropriate partner countries
LOCAL COMMUNITIES

## Slide 8
We will
- use website and the NING to showcase the experiences and outcomes achieved during the project
- produce articles for appropriate journals
- share practice sessions within learning communities
- disseminate results and informations at conferences within each European country/region
- disseminate informations where applicable to Local Authority bodies and Government agencies
- develop Case Study example available for use by other organisations/schools
WIDER LIFELONG LEARNING COMMUNITY

## Slide 9
DURING EACH TRANSNATIONAL MOBILITY

## Slide 10
1) The host partnerschool will
- organise a planned programme for the visit
ensure students and teachers participate in lessons
arrange a project meeting to
  review previous work and NING content
  make evaluations/questionnaires to be completed one month after each mobility
  help each school to produce video diary with a specific curriculum aim (e.g. sporting activities across the partnership, UK Olympics in 2012 will be a common bond of all participants in the project.
DURING EACH TRANSNATIONAL MOBILITY

## Slide 11
2) All partner schools will
host a project meeting involving 20-30 students and about 10 staff
enable the use of IT facilities for the common delivery of information to the proposed NING
complete a 'Livre d'Or‘ as part of the on-going evaluation process.
prepare school newsletters and websites to provide pupil feedback on experiences during mobilities
prepare a report of each mobility - details of the country visited, the focus of the visit, the activities that took place and any impact or outcomes that occurred.
will provide real sources of information and data : healthy school data, careers guidance, sporting activities, photograph competition, interviews of sportsmen and women which can be used by teachers in their lessons
  publish the report on the school web-site and NING site
  make video diaries providing an on-going record of the project progress

## Slide 12
3) Host families will
- have an important part to play in the transnational mobilities
give the students of the different partner schools the possibility to gain experiences by living with their host for a short period of time. This experience should not be overlooked or underestimated
give their feedback in a questionnaire which will be standard for all partner schools
help build further the partnerships between schools and parents

## Slide 13
13
13
in Collège du Sacré-Coeur, La Ville du Bois, France, 14-17 September 2011
COORDINATORS meeting
Previous Comenius Project Different Numbers : common final report with all the coordinators
New Project Going for Gold 2011-2013 :
  Presentation
  Preparation of the programme for the 2 years :
    Planning of the activities
    Planning of the mobilities
    Individual Mobility : Presentation of a student coming from the Spanish partner school
Visit of the ISC School
Cultural visit in Paris
DURING MOBILITY 1

## Slide 14
in NMS Europaschule, WienerNeustadt, Autriche, 4-11 March 2012
STUDENTS will
make their presentation of their country, town and school : Sport, leisure in the curriculum, careers option
participate in classes
work in European groups on tasks related to
  sport,
  healthy lifestyles
  work-life balance
  produce video diary "On the ski slopes"
14
DURING MOBILITY 2

## Slide 15
15
in Braunton and Pilton Schools and Community Colleges, UK, 12-17 June 2012
STUDENTS will
make their presentation about : our Olympics hopes in our country
participate in classes, lessons and European groups to complete a challenge enabling them to plan and complete their own alternative Olympics
work in European groups on tasks related to
  sport
  healthy lifestyles
  work-life balance and UK Olympics in 2012
  produce video diary "Our countries Olympic hopes"
DURING MOBILITY 3

## Slide 16
16
in Collège du Sacré-Coeur, La Ville du Bois, France, 16-21 October 2012
STUDENTS will
make their presentation of their country, town and school : “My school is a healthy school because …”
participate in classes
work in European groups on tasks related to
  sport
  healthy lifestyles
  work-life balance
  produce video diary “Healthy schools“
  decide who gets “The healthy school award”
DURING MOBILITY 4

## Slide 17
17
in Lycée Joseph Gaillard, Fort de France, Martinique, 9-16 March 2013
STUDENTS will
make their presentation about “ The world of work- locally, nationally and across Europe”
participate in classes
work in European groups on tasks related to
  sport
  healthy lifestyles
  work-life balance
  produce video diary " Our world of work"
DURING MOBILITY 5

## Slide 18
18
in Børstad Ungdomsskole, Hamar, Norvège, 14-19 May 2013
STUDENTS will
make their presentation about “The importance of being an European Citizen”
participate in classes
work in European groups on tasks related to
  sport
  healthy lifestyles
  work-life balance
  produce video diary " Being an European Citizen"
DURING MOBILITY 6

## Slide 19
Joyeux Noël - Bonne Année 2012
Frohe Weihnachten - Glückliches Neujahr 2012
Going For Gold
Merry Christmas - Happy New Year 2012
Head : M. BRAILLY
Coordination : Mrs Lavollée
Team, students and families